## Project Gantt
PRODUCT DELIVERY PLAN — EXAMPLE
Reusable delivery planning template for a Product Owner, two Developers and QA
Project |  |  |  | Baseline start |  |  | Status date |  |  | Target release |  |  | Working days/week
Customer Experience Release |  |  |  | 2026-08-03 |  |  | 2026-08-20 |  |  | 2026-09-18 |  |  | 5
[14 empty] | Aug 2026 | [28 empty] | Sep 2026
WBS | Work item | Type | Owner | Start | Duration (days) | Finish | Predecessor | Priority | Progress | Status | Effort (hours) | Schedule flag | Notes | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18
1.0 | Discovery and project baseline | Phase | Product Owner | 2026-08-03 | 5 |  |  | High | 100% | Done | 20 |  | Clarify scope, stakeholders and measurable outcomes.
1.1 | Stakeholder interviews | Task | Product Owner | 2026-08-03 | 2 |  |  | High | 100% | Done | 12 |  | Interview sales, support and operations.
1.2 | Product vision and success metrics | Task | Product Owner | 2026-08-05 | 2 |  | 1.1 | High | 100% | Done | 8 |  | Define adoption, conversion and support-volume targets.
1.3 | Release roadmap approval | Milestone | Product Owner | 2026-08-07 | 1 |  | 1.2 | Critical | 100% | Done | 2 |  | Baseline approved by stakeholders.
2.0 | Feature A — Customer onboarding | Phase | Developer 1 | 2026-08-10 | 15 |  | 1.3 | Critical | 75% | In progress | 0 |  | First shippable feature.
2.1 | Refine onboarding stories | Task | Product Owner | 2026-08-10 | 2 |  | 1.3 | High | 100% | Done | 10 |  | Acceptance criteria and edge cases.
2.2 | Design onboarding data model | Task | Developer 1 | 2026-08-12 | 3 |  | 2.1 | High | 100% | Done | 20 |  | Entities, validation and migration assumptions.
2.3 | Build onboarding API | Task | Developer 1 | 2026-08-15 | 5 |  | 2.2 | Critical | 80% | In progress | 36 |  | Service layer, validation and tests.
2.4 | Build onboarding UI | Task | Developer 2 | 2026-08-15 | 5 |  | 2.2 | Critical | 70% | In progress | 36 |  | Responsive flow and client-side validation.
2.5 | Integration and code review | Task | Developer 1 | 2026-08-20 | 2 |  | 2.3, 2.4 | Critical | 30% | In progress | 20 |  | Merge API and UI and resolve review comments.
2.6 | QA test design — onboarding | Task | QA | 2026-08-17 | 3 |  | 2.1 | High | 80% | In progress | 20 |  | Positive, negative, accessibility and regression cases.
2.7 | QA execution — onboarding | Task | QA | 2026-08-22 | 3 |  | 2.5, 2.6 | Critical | 0% | Not started | 24 |  | Functional and regression execution.
2.8 | Feature A accepted | Milestone | Product Owner | 2026-08-25 | 1 |  | 2.7 | Critical | 0% | Not started | 4 |  | PO validates acceptance criteria.
3.0 | Feature B — Notifications | Phase | Developer 2 | 2026-08-17 | 16 |  | 1.3 | High | 35% | In progress | 0 |  | Second feature developed partly in parallel.
3.1 | Refine notification stories | Task | Product Owner | 2026-08-17 | 2 |  | 1.3 | High | 100% | Done | 8 |  | Channels, templates and opt-out rules.
3.2 | Notification architecture spike | Task | Developer 2 | 2026-08-19 | 3 |  | 3.1 | High | 100% | Done | 20 |  | Select asynchronous processing pattern.
3.3 | Build notification service | Task | Developer 2 | 2026-08-22 | 5 |  | 3.2 | Critical | 50% | In progress | 36 |  | Queueing, templates and retry behavior.
3.4 | Build notification preferences UI | Task | Developer 1 | 2026-08-26 | 4 |  | 3.1 | High | 10% | In progress | 28 |  | User preferences and validation.
3.5 | Integration and code review | Task | Developer 2 | 2026-08-30 | 2 |  | 3.3, 3.4 | Critical | 0% | Not started | 20 |  | Integrate and review.
3.6 | QA test design — notifications | Task | QA | 2026-08-26 | 3 |  | 3.1 | High | 20% | In progress | 20 |  | Delivery, retry, preferences and regression.
3.7 | QA execution — notifications | Task | QA | 2026-09-01 | 3 |  | 3.5, 3.6 | Critical | 0% | Not started | 24 |  | Functional and regression execution.
3.8 | Feature B accepted | Milestone | Product Owner | 2026-09-04 | 1 |  | 3.7 | Critical | 0% | Not started | 4 |  | PO validates acceptance criteria.
4.0 | Release hardening and launch | Phase | QA | 2026-09-05 | 10 |  | 2.8, 3.8 | Critical | 0% | Not started | 0 |  | Cross-feature release readiness.
4.1 | End-to-end regression | Task | QA | 2026-09-05 | 4 |  | 2.8, 3.8 | Critical | 0% | Not started | 32 |  | Full business flow regression.
4.2 | Defect correction buffer | Task | Developer 1 | 2026-09-09 | 3 |  | 4.1 | Critical | 0% | Not started | 24 |  | Shared buffer across both developers.
4.3 | Release notes and training material | Task | Product Owner | 2026-09-07 | 3 |  | 2.8, 3.8 | Medium | 0% | Not started | 12 |  | Audience, impact and known limitations.
4.4 | Production readiness review | Milestone | Product Owner | 2026-09-12 | 1 |  | 4.2, 4.3 | Critical | 0% | Not started | 4 |  | Go/no-go decision.
4.5 | Production deployment | Milestone | Developer 1 | 2026-09-13 | 1 |  | 4.4 | Critical | 0% | Not started | 4 |  | Controlled production release.
4.6 | Hypercare and KPI review | Task | Product Owner | 2026-09-14 | 5 |  | 4.5 | High | 0% | Not started | 16 |  | Monitor incidents, adoption and outcome metrics.

## Team Capacity
TEAM CAPACITY
Role | Available hours | Assigned hours | Utilization | Capacity flag | Week 1 | Week 2 | Week 3 | Week 4 | Week 5
Product Owner | 120
Developer 1 | 200
Developer 2 | 200
QA | 160

## RAID Log
RAID LOG — RISKS, ASSUMPTIONS, ISSUES AND DEPENDENCIES
ID | Type | Description | Probability | Impact | Score | Owner | Mitigation / response | Due date | Status
R-01 | Risk | QA becomes the bottleneck when both features reach test simultaneously. | 4 | 5 |  | QA | Move test design earlier; reserve regression capacity; developers support automation. | 2026-08-21 | Open
R-02 | Risk | Notification provider sandbox is unstable. | 3 | 4 |  | Developer 2 | Use a deterministic mock and keep provider validation outside the critical path. | 2026-08-19 | Mitigating
A-01 | Assumption | Product Owner can answer story questions within one business day. | 2 | 4 |  | Product Owner | Escalate unanswered decisions in the daily checkpoint. | 2026-08-14 | Accepted
D-01 | Dependency | Security review must finish before production readiness. | 3 | 5 |  | Developer 1 | Book review in week two and provide architecture evidence early. | 2026-09-09 | Open
I-01 | Issue | Onboarding accessibility defects found during early QA. | 4 | 3 |  | Developer 2 | Correct keyboard focus and error announcements before integration review. | 2026-08-24 | In progress

## How to Use
HOW TO USE THIS TEMPLATE
Step | Area | Instruction
1 | Update the project controls | Change Project, Baseline start, Status date, Target release and Working days/week in the Project Gantt sheet.
2 | Edit the work breakdown structure | Replace the example rows with phases, tasks and milestones. Keep WBS identifiers unique.
3 | Assign owners and effort | Choose Product Owner, Developer 1, Developer 2 or QA and enter estimated effort in hours.
4 | Maintain dates and dependencies | Start and Duration are inputs. Finish is calculated with WORKDAY. Use Predecessor as a readable reference.
5 | Track delivery progress | Update Progress and Status. The green portion of each bar represents completed work; blue represents remaining work.
6 | Review capacity | The Team Capacity sheet compares assigned effort with available hours and flags potential over-allocation.
7 | Maintain the RAID log | Record risks, assumptions, issues and dependencies with owners, mitigation actions and due dates.
8 | Use in Excel, Google Sheets or LibreOffice | The workbook uses standard formulas and formatting. On import, allow the application to recalculate formulas.